## Summary
Kalman Filter Investment Research Project — Updated Log
Field | Current Value / Decision
Last updated | 2026-05-30
Verified SPY data range | 2015-01-01 through 2026-05-29
Current project stage | Tuning paused; moving to reusable code, batch testing, and validation
Current shared ETF baseline | q_jerk=1e-7, r_meas=5e-4, buySignal=trend_est>0, sellSignal=trend_high<0, buyConfirmDays=5, sellConfirmDays=8
Transaction cost | 0.001 per trade
Best SPY in-sample result | 432.29% return, -24.07% max DD, Sharpe 1.03, 13 trades, 96.65% time in market
ETF setting conclusion | Shared ETF candidate remains r_meas=5e-4; QQQ-specific alternative may be r_meas=7.5e-4
Single-stock conclusion | Current ETF-tuned settings do not transfer cleanly to MSFT/NVDA; later stock branch should use separate/adaptive logic
Latest code architecture | Converted step1.m into reusable runKalmanTrendModel(filename, params)
Default function flags | params.makePlots=true and params.printSummary=true; set both false for quiet batch runs
Next recommended step | Create runBatchKalmanTests.m, reproduce known results, then move to walk-forward validation

## Change Log
Detailed Change Log
Every significant code/model/test change tracked so future exports remain reproducible.
ID | File | Section / Area | Old Behavior | New Behavior / Change | Reason | Result / Status
001 | step1.m | Plot 4 legend | legend("Price","Position","Location","best") | Handle-based legend: legend([hPrice,hPosition],{Price,Position},Location,best) | MATLAB interpreted Position as a legend property name | Fixed legend error
002 | step1.m | Signal logic | Immediate switching on trend confidence crossings | Added confirmation-day logic | Reduce rapid position flipping | Cleaner signal
003 | step1.m | Signal diagnostics | No quick trade diagnostics | Added tradeCount and timeInMarket outputs | Quantify signal activity | Used throughout tuning
004 | step1.m | Tuning parameters | q_jerk=1e-7 only | Tested lower q_jerk values | Check whether smoother process noise reduces trades | Lower q_jerk increased trade count; reverted to 1e-7
005 | step1.m | Signal logic | 5 confirmation days baseline | Tested confirmDays=10 | Reduce overtrading | Trades dropped to 9; time in market 65.41%
006 | step1.m | Signal logic | 5 confirmation days baseline | Tested confirmDays=15 | Check conservative limit | Only 1 trade; too restrictive
007 | step1.m | Signal diagnostics/results | Only total trade count | Added action labels: Buy, Sell, Hold Long, Hold Cash | Separate buy/sell actions | Improved interpretability
008 | step1.m | Signal logic | Symmetric buy/sell confirmation | Proposed asymmetric rules | Address lag and early exits | Led to later signal tests
009 | step1.m | Backtest diagnostics | No strategy performance metrics | Added total return, max drawdown, Sharpe, transaction costs | Tune by metrics, not plots only | Backtest metrics became standard
010 | step1.m | Plots | Price confidence plot had been replaced | Restored price estimate with 90% CI as Plot 1 | Keep both CI plot and buy/sell marker plot | Six-plot structure restored
011 | step1.m | Sell signal | sellSignal = trend_est < 0 | Tested buffered sell rule using sellBuffer | Avoid selling on tiny trend noise | Still too little time in market
012 | step1.m | Signal loop | Buy/sell counters always active | Made loop position-aware | Only count buys while in cash and sells while long | Cleaner logic
013 | step1.m | Sell buffer test | No buffer | sellBuffer=-0.00025 | Test sell patience | Return 13.44%, Sharpe 0.34, time 3.66%
014 | step1.m | Sell buffer test | No buffer | sellBuffer=-0.0005 | Test sell patience | Return 26.39%, Sharpe 0.57, time 5.23%
015 | step1.m | Sell buffer test | No buffer | sellBuffer=-0.001 | Test sell patience | Return 26.85%, Sharpe 0.58, time 5.26%
016 | step1.m | Sell signal | sellSignal = trend_est < buffer | sellSignal = trend_high < 0 | Sell only when trend CI is fully negative | Improved exposure and performance
017 | step1.m | Signal result | Buffered sell rules | Confidence-based sell rule | Reduce premature sells | Return 67.76%, Sharpe 0.78, time 23.88%
018 | step1.m | Comments | Comment referenced negative sell buffer | Updated comment to CI-based sell rule | Keep code comments accurate | Cleanup
019 | step1.m | Buy signal | buySignal = trend_low > 0 | Proposed buySignal = trend_est > 0 | Current buy rule too strict | Moved to more realistic market exposure
020 | step1.m | Buy signal | trend_low > 0 | trend_est > 0 | Relax buy rule | Market participation increased
021 | step1.m | Buy confirm sweep | buyConfirmDays=10/15 | Tested buyConfirmDays=5 | Find better buy responsiveness | Best return among buy tests: 299.58%, Sharpe 0.95
022 | step1.m | Buy confirm sweep | buyConfirmDays=5 | Tested buyConfirmDays=10 | Compare responsiveness | Return 180.12%, Sharpe 0.81
023 | step1.m | Buy confirm sweep | buyConfirmDays=5 | Tested buyConfirmDays=15 | Defensive alternative | Return 145.11%, Sharpe 0.86, lower DD
024 | step1.m | Backtest diagnostics | Only strategy max DD/Sharpe | Added buy-hold max DD and buy-hold Sharpe | Fair benchmark comparison | Used in later runs
025 | step1.m | Sell confirm sweep | sellConfirmDays=5 baseline | Started sellConfirmDays sweep 5-10 | Early sells still observed | Identified 7-8 day sweet spot
026 | step1.m | Sell confirm sweep | sCD=5 baseline | Tested sCD=6 | Check sell patience | Return 326.88%, Sharpe 0.95
027 | step1.m | Sell confirm sweep | sCD=6 | Tested sCD=7 | Check sell patience | Return 388.19%, Sharpe 1.01, best DD -22.54%
028 | step1.m | Sell confirm sweep | sCD=7 | Tested sCD=8 | Check sell patience | Best current SPY in-sample return 417.99%, Sharpe 1.03
029 | step1.m | Sell confirm sweep | sCD=8 | Tested sCD=9 | Check sell patience limit | Performance fell; DD worsened to -32.24%
030 | step1.m | Sell confirm sweep | sCD=9 | Tested sCD=10 | Check buy-hold-like behavior | Too slow to exit; DD -35.17%
031 | step1.m | Measurement tuning | r_meas=1e-4 baseline | Tested r_meas=5e-5 | Check lower measurement noise | Too reactive: return 286.32%, Sharpe 0.82
032 | step1.m | Measurement tuning | r_meas=1e-4 baseline | Confirmed r_meas=1e-4 | Baseline measurement noise | Return 417.99%, Sharpe 1.03
033 | step1.m | Measurement tuning | r_meas=1e-4 baseline | Tested r_meas=5e-4 | Check higher measurement noise | Best SPY candidate: 432.29%, Sharpe 1.03
034 | step1.m | Measurement tuning | r_meas=5e-4 | Tested r_meas=1e-3 | Check conservative limit | Too buy-and-hold-like: only 5 trades
035 | step1.m | Local r sweep | r_meas=5e-4 | Tested r_meas=2.5e-4 | Local robustness check | Return 388.98%, Sharpe 0.97
036 | step1.m | Local r sweep | r_meas=5e-4 | Retested r_meas=5e-4 | Local benchmark | Best local result
037 | step1.m | Local r sweep | r_meas=5e-4 | Tested r_meas=7.5e-4 | Local robustness check | Close result but more buy-and-hold-like
038 | step1.m | Cross-asset validation | Assumed r_meas=5e-4 | Discovered earlier cross-asset run used r_meas=7.5e-4 | Correct the record | Earlier run relabeled as 7.5e-4 validation
039 | step1.m | Cross-asset validation | No official 5e-4 cross-asset set | Reran SPY/QQQ/SPYG/MSFT/NVDA at r_meas=5e-4 | Validate current SPY-best setting | SPY/SPYG strong; QQQ mixed; MSFT/NVDA weak
040 | step1.m | ETF interpretation | Results scattered across tests | Added ETF-specific r_meas comparison summary for 5e-4 vs 7.5e-4 | Decide shared ETF setting | 5e-4 remains shared ETF candidate; QQQ may prefer 7.5e-4
041 | step1.m | Tuning plan | Continue per-asset tuning | Set tuning aside for now | Avoid overfitting | Move to reusable code and validation
042 | runKalmanTrendModel.m | Code architecture | Single long script requiring manual filename/parameter edits | Converted into function runKalmanTrendModel(filename, params) | Reusable tests and future walk-forward validation | Function created
043 | runKalmanTrendModel.m | Function inputs | Filename hard-coded in script | filename required; params optional | Simple use now; tweakable later | Supports defaults and overrides
044 | runKalmanTrendModel.m | Output controls | Plots and prints always produced | Added params.makePlots and params.printSummary flags | Quiet batch operation | Use false/false for batch tests
045 | runBatchKalmanTests.m | Next planned file | Manual one-ticker runs | Plan batch runner across tickers | Reproduce results consistently and export summary | Next step

## Signal Sweeps
Signal Confirmation Sweeps
SPY in-sample 2015-01-01 to 2026-05-29; q_jerk=1e-7, r_meas=1e-4 before measurement-noise sweep.
sellConfirmDays | Buy Count | Sell Count | Strategy Return % | Buy-Hold Return % | Strategy Max DD % | Buy-Hold Max DD % | Strategy Sharpe | Buy-Hold Sharpe | Trade Count | Time in Market % | Interpretation
5 | 30 | 29 | 299.58 | 339.63 | -23.03 | -33.72 | 0.95 | 0.83 | 59 | 87.45 | Baseline; sells too quickly
6 | 21 | 20 | 326.88 | 339.63 | -25.83 | -33.72 | 0.95 | 0.83 | 41 | 91.42 | Improved return, fewer trades
7 | 14 | 13 | 388.19 | 339.63 | -22.54 | -33.72 | 1.01 | 0.83 | 27 | 94.11 | Best drawdown
8 | 11 | 10 | 417.99 | 339.63 | -23.58 | -33.72 | 1.03 | 0.83 | 21 | 95.47 | Best return/Sharpe before r_meas tuning
9 | 9 | 8 | 312.72 | 339.63 | -32.24 | -33.72 | 0.84 | 0.83 | 17 | 96.48 | Too much time in market
10 | 6 | 5 | 254.26 | 339.63 | -35.17 | -33.72 | 0.74 | 0.83 | 11 | 98.12 | Too slow to exit

## Measurement Sweeps
Measurement Noise Sweeps
SPY in-sample 2015-01-01 to 2026-05-29; q_jerk=1e-7, buySignal=trend_est>0, sellSignal=trend_high<0, buyConfirmDays=5, sellConfirmDays=8.
r_meas | Buy Count | Sell Count | Strategy Return % | Buy-Hold Return % | Strategy Max DD % | Buy-Hold Max DD % | Strategy Sharpe | Buy-Hold Sharpe | Trade Count | Time in Market % | Interpretation
5e-5 | 15 | 14 | 286.32 | 339.63 | -32.39 | -33.72 | 0.82 | 0.83 | 29 | 94.42 | Too reactive
1e-4 | 11 | 10 | 417.99 | 339.63 | -23.58 | -33.72 | 1.03 | 0.83 | 21 | 95.47 | Strong baseline
2.5e-4 | 9 | 8 | 388.98 | 339.63 | -25.95 | -33.72 | 0.97 | 0.83 | 17 | 96.86 | Decent, worse than 5e-4
5e-4 | 7 | 6 | 432.29 | 339.63 | -24.07 | -33.72 | 1.03 | 0.83 | 13 | 96.65 | Current best SPY/shared ETF candidate
7.5e-4 | 4 | 3 | 425.79 | 339.63 | -25.42 | -33.72 | 1 | 0.83 | 7 | 98.15 | Close, more buy-and-hold-like
1e-3 | 3 | 2 | 414.64 | 339.63 | -24.5 | -33.72 | 0.99 | 0.83 | 5 | 98.43 | Too conservative

## Cross Asset Tests
Cross-Asset Test Results
Includes official r_meas=5e-4 run and corrected earlier r_meas=7.5e-4 run.
Run | Ticker | r_meas | Buy Count | Sell Count | Strategy Return % | Buy-Hold Return % | Strategy Max DD % | Buy-Hold Max DD % | Strategy Sharpe | Buy-Hold Sharpe | Trade Count | Time in Market % | Verdict
Official 5e-4 | SPY | 5e-4 | 7 | 6 | 432.29 | 339.63 | -24.07 | -33.72 | 1.03 | 0.83 | 13 | 96.65 | Strong
Official 5e-4 | QQQ | 5e-4 | 14 | 13 | 626.55 | 676.99 | -29.26 | -35.12 | 1.01 | 0.93 | 27 | 93.2 | Mixed: return lower, risk-adjusted better
Official 5e-4 | SPYG | 5e-4 | 9 | 8 | 621.95 | 456.73 | -24.72 | -32.68 | 1.08 | 0.85 | 17 | 94.74 | Very strong
Official 5e-4 | MSFT | 5e-4 | 21 | 20 | 688.79 | 1019.95 | -40.42 | -37.15 | 0.88 | 0.92 | 41 | 90.2 | Weak
Official 5e-4 | NVDA | 5e-4 | 41 | 40 | 9324.86 | 43601.97 | -57.01 | -66.34 | 1.15 | 1.35 | 81 | 84.1 | Weak for upside
Earlier 7.5e-4 | SPY | 7.5e-4 | 4 | 3 | 425.79 | 339.63 | -25.42 | -33.72 | 1 | 0.83 | 7 | 98.15 | Strong but more buy-hold-like
Earlier 7.5e-4 | QQQ | 7.5e-4 | 12 | 11 | 719.7 | 676.99 | -30.86 | -35.12 | 1.06 | 0.93 | 23 | 93.86 | Strong
Earlier 7.5e-4 | SPYG | 7.5e-4 | 9 | 8 | 549.47 | 456.73 | -29.95 | -32.68 | 1.03 | 0.85 | 17 | 94.91 | Strong
Earlier 7.5e-4 | MSFT | 7.5e-4 | 15 | 14 | 1004.29 | 1019.95 | -34.22 | -37.15 | 0.99 | 0.92 | 29 | 93.24 | Mixed
Earlier 7.5e-4 | NVDA | 7.5e-4 | 37 | 36 | 7745.36 | 43601.97 | -61.39 | -66.34 | 1.11 | 1.35 | 73 | 84.9 | Weak for upside

## ETF r Comparison
ETF-Specific r_meas Comparison
Organized comparison of existing ETF results for r_meas=5e-4 vs 7.5e-4.
ETF | r_meas | Strategy Return % | Buy-Hold Return % | Strategy Max DD % | Buy-Hold Max DD % | Strategy Sharpe | Buy-Hold Sharpe | Trade Count | Time in Market % | Preferred? | Notes
SPY | 5e-4 | 432.29 | 339.63 | -24.07 | -33.72 | 1.03 | 0.83 | 13 | 96.65 | Yes | Best SPY choice
SPY | 7.5e-4 | 425.79 | 339.63 | -25.42 | -33.72 | 1 | 0.83 | 7 | 98.15 | No | Close, but weaker Sharpe/DD
QQQ | 5e-4 | 626.55 | 676.99 | -29.26 | -35.12 | 1.01 | 0.93 | 27 | 93.2 | No | Risk-adjusted improvement but lower return
QQQ | 7.5e-4 | 719.7 | 676.99 | -30.86 | -35.12 | 1.06 | 0.93 | 23 | 93.86 | Possible | QQQ-specific alternative
SPYG | 5e-4 | 621.95 | 456.73 | -24.72 | -32.68 | 1.08 | 0.85 | 17 | 94.74 | Yes | Best SPYG choice
SPYG | 7.5e-4 | 549.47 | 456.73 | -29.95 | -32.68 | 1.03 | 0.85 | 17 | 94.91 | No | Worse return/DD/Sharpe
Average | 5e-4 | 560.26 |  | -26.02 |  | 1.04 |  | 19 | 94.86 | Shared candidate | Better average drawdown/Sharpe
Average | 7.5e-4 | 564.99 |  | -28.74 |  | 1.03 |  | 15.67 | 95.64 | Alternative | Slightly higher avg return but worse DD/Sharpe

## Function Refactor
Function Refactor and Reusable Workflow
Current reusable function architecture and next coding step.
Feature | Implementation | Reason / Usage
Function name | runKalmanTrendModel(filename, params) | Reusable model runner for one CSV/ticker
Required input | filename | Simple current workflow: run one ticker by file
Optional input | params struct | Allows parameter overrides without editing function source
Default q_jerk | 1e-7 | Current baseline
Default r_meas | 5e-4 | Current shared ETF candidate
Default buy rule | trend_est > 0 | Semi-strict buy rule from tuning
Default sell rule | trend_high < 0 | Confidence-based sell rule
Default buyConfirmDays | 5 | Best current buy confirmation setting
Default sellConfirmDays | 8 | Best current SPY in-sample sell confirmation setting
Default transactionCost | 0.001 | 0.1% per trade
Plot flag | params.makePlots | Set false for quiet batch runs
Print flag | params.printSummary | Set false to suppress Command Window summary
Outputs | results, summary, figs | Full table, metrics struct, figure handles
Next script | runBatchKalmanTests.m | Run multiple tickers and export comparison summary